## Übersicht & Aufgaben
Document | Purpose
Project Brief | Provides a high-level overview of the project’s purpose, objectives, scope and approach to secure initial approval
Project Product Description | Defines the final product’s purpose, composition, quality expectations and acceptance criteria
Daily Log | A record used to capture informal issues, risks, and project notes during day-to-day activities
Lessons Log | A repository of lessons learned and potential improvements captured throughout the project
Business Case | Justifies the investment by explaining the project’s benefits, costs, risks, and alignment with business strategy
Benefits Management Approach | Outlines how and when the project’s expected benefits will be measured and realized
Project Initiation Documentation (PID) | Consolidates key baseline information about the project’s objectives, scope, governance and delivery plans
Project Plan | Provides the overall schedule, resources, costs and controls for delivering the project
Stage Plan | Details how a particular management stage will be executed, monitored and controlled
Team Plan | Describes how a team will produce specific work packages within agreed constraints
Communication Management Approach | Defines how stakeholders will be kept informed and engaged during the project
Configuration Management Approach | Describes how the project’s products and their versions will be controlled and tracked
Quality Management Approach | Sets out the project’s quality standards, procedures, roles, and responsibilities
Risk Management Approach | Defines how risks will be identified, assessed, controlled, and reported
Change Control Approach | Explains how changes to project scope or products will be proposed, assessed and managed
Checkpoint Report | Provides a snapshot of progress, issues and forecasts from a teammanager to the Project Manager
Highlight Report | A regular summary for the Project Board on stage progress, risks and issues
Issue Report | Documents details of a formal issue, its impact, options and recommendations
Risk Register | A structured record of all identified risks, their assessments and responses
Issue Register | A log of all formal project issues and their current status
Quality Register | Tracks all planned and completed quality control and assurance activities
Product Descriptions | Define the purpose, composition, quality criteria and method of production for individual products
Configuration Item Records | Contain details of each product’s version, status and relationship to other products
Change Log | Records requests for change and decisions made throughout the project lifecycle
End Project Report | Summarizes project performance, outcomes and lessons compared to the original plan
End Stage Report | Provides the Project Board with a review of stage performance and justification to proceed
Lessons Report | Captures and analyzes lessons learned for future projects and organizational improvement
Benefits Review Plan | Defines how and when benefits will be reviewed after project closure

## Project Brief
Background | Explains why the project is needed and the context that led to its proposal
Project Objectives | States what the project aims to achieve in terms of outputs, outcomes and benefits
Project Scope | Defines what is included and excluded from the project
Constraints | Lists any restrictions that must be respected like budget, deadlines, resources and comapny standards
Assumptions | Highlights key assumptions underpinning the project planning
Project Tolerances | Outlines allowable deviations for time, cost, scope and quality
Outline Business Case | Summarizes reasons, expected benefits, costs and risks of the project
Project Product Description | Defines purpose, composition, quality expectations and acceptance criteria of the final product
Project Approach | Describes the chosen method or strategy to create the products
Project Management Team Structure | Defines the governance structure and roles for project delivery
Role Descriptions | Provides brief descriptions of each key role and responsibilities
References | Lists any supporting strategies, policies or reference materials

## Project Product Description
Purpose | States the reason for creating the final product
Composition | Lists the main components of the final product
Derivation | Explains the source of requirements or inputs
Quality Expectations | Describes what stakeholders expect in terms of quality
Acceptance Criteria | Defines the conditions that must be met for acceptance
Acceptance Method | Explains how the product will be tested and accepted

## Daily Log
Informal Issues | Captures small issues that don’t require formal escalation
Risks/Opportunities | Notes informal risks or opportunities spotted during work
Events/Decisions | Records key day-to-day decisions or events
Observations | Holds ad hoc comments, reminders or lessons noted by the project manager

## Lessons Log
Lesson ID | Unique identifier for the lesson learned
Lesson Description | Short description of the lesson identified
Source | Notes where the lesson originated
Potential Application | Explains how the lesson could be applied in future work

## Business Case
Reasons | Explains the justification for undertaking the project
Business Options | Presents possible approaches, including "do nothing", "do the minimum" or "do something"
Expected Benefits | Describes measurable improvements resulting from the project
Expected Dis-benefits | Identifies potential negative outcomes
Timescale | Provides an outline of delivery schedule and benefit realization timeline
Costs | Estimates overall project and operational costs
Investment Appraisal | Compares costs vs. benefits to support decision-making
Major Risks | Summarizes significant risks that could impact success

## Benefits Management Approach
Purpose | Explains how benefits will be managed and measured
Responsibilities | Defines who is responsible for tracking and realizing benefits
Timescales | Specifies when benefits will be reviewed and achieved
Methods | Outlines techniques and processes for measuring benefits
Review Plan | Schedules benefits reviews post-project

## Project Initiation Documentatio
Project Definition | Explains the purpose, objectives, scope, constraints and tolerances
Project Approach | Defines the delivery strategy and design decisions
Business Case | Provides the detailed justification for the project
Project Management Team Structure | Defines governance roles and responsibilities
Role Descriptions | Summarizes responsibilities for each project role
Quality Management Approach | Describes how quality will be managed and assured
Risk Management Approach | Defines how risks will be identified, assessed, and controlled
Change Control Approach | Explains how changes will be handled and tracked
Communication Management Approach | Defines how information will be shared with stakeholders
Project Plan | Provides the overall schedule, costs and resource plan
Tailoring of PRINCE2 | Explains how PRINCE2 will be adapted for the project

## Project Plan
Plan Description | Explains purpose, scope, assumptions and constraints of the plan
Plan Prerequisites | Lists conditions that must be met before execution
External Dependencies | Identifies links to other projects or organizations
Planning Assumptions | Notes assumptions made in planning activities
Product Breakdown Structure | Shows hierarchy of products to be delivered
Product Descriptions | Defines key product details and quality expectations
Product Flow Diagram | Illustrates sequence of product development
Schedule | Provides activities, dependencies, and milestones
Resource Requirements | Details resource needs across the plan
Budget | Summarizes planned costs and allocations
Tolerances | Defines limits for time, cost, and scope deviations
Monitoring and Control | Explains how progress will be tracked and reported

## Stage Plan
Purpose | Describes how a specific stage will be executed and controlled
Products | Lists products to be created in this stage
Schedule | Details activities, milestones, and dependencies for this stage
Resources | Defines staff, materials, and tools required
Tolerances | Specifies permissible deviation for time and cost in the stage

## Team Plan
Purpose | Explains how a team will deliver assigned work packages
Products | Lists deliverables assigned to the team
Activities | Details the tasks needed to complete work packages
Resources | Defines required staff, skills and effort
Schedule | Provides timeline for team-level delivery

## Communication Management Approa
Purpose | Defines how stakeholders will be informed and engaged
Stakeholder Analysis | Identifies stakeholders and their communication needs
Information Needs | Specifies what information is needed by whom
Communication Methods | Describes methods (reports, meetings, etc.)
Frequency | Details when communications will take place

## Configuration Management Approa
Purpose | Explains how products will be controlled and tracked.
Configuration Management Procedure | Outlines processes for identifying and tracking items.
Tools and Techniques | Lists tools to support configuration management.
Records | Specifies what records will be kept.
Responsibilities | Defines who will manage product configurations.

## Quality Management Approach
Purpose | Defines how project quality will be assured and controlled
Quality Standards | Specifies applicable standards and criteria
Quality Responsibilities | Identifies roles responsible for quality assurance
Quality Control Techniques | Outlines methods for testing and reviews
Quality Records | Details how quality checks will be documented

## Risk Management Approach
Purpose | Explains how risks will be identified, assessed, and managed
Risk Tolerances | Defines acceptable levels of risk exposure
Risk Roles and Responsibilities | Specifies who manages risks at each level
Risk Procedures | Describes methods for identifying, assessing and responding
Risk Reporting | Explains how risks will be monitored and reported

## Change Control Approach
Purpose | Explains how changes will be identified, assessed and controlled
Change Authority | Defines who is authorized to approve changes
Change Control Procedure | Outlines steps for handling change requests
Records | Specifies how changes will be logged and tracked
Reporting | Explains how changes will be communicated

## Checkpoint Report
Work Package Progress | Summarizes progress against assigned tasks
Quality Information | Reports on product quality checks completed
Problems and Issues | Notes any difficulties or risks raised
Forecast | Provides updated estimate of completion for tasks

## Highlight Report
Current Stage Progress | Summarizes performance in the current stage
Risks and Issues | Highlights significant risks and issues
Next Period Forecast | Provides expectations for the next reporting period
Overall Project Status | Assesses whether the project is on track

## Issue Report
Issue Description | Details the nature of the issue raised
Impact Assessment | Analyzes impact on project objectives
Options | Lists possible responses to the issue
Recommendation | Proposes preferred resolution for decision-making

## Risk Register
Risk ID | Unique identifier for each risk
Description | Summarizes the risk event
Cause | Explains the source of the risk
Impact | Describes consequences if the risk occurs
Probability | Rates likelihood of occurrence
Response | Defines actions to address the risk
Owner | Names who is responsible for managing the risk

## Issue Register
Issue ID | Unique identifier for each issue
Description | Summarizes the issue raised
Impact | Explains impact on project objectives
Status | Shows current handling progress
Owner | Specifies who is managing the issue

## Quality Register
Quality Activity | Lists planned and completed quality checks
Product | Specifies which product the activity relates to
Date | Records when the activity occurred
Outcome | Notes results of the quality check
Follow-up | Specifies actions required to resolve issues

## Product Descriptions
Purpose | Explains the need for the product
Composition | Lists components making up the product
Derivation | Shows input sources for the product
Format/Presentation | Specifies form and presentation of the product
Quality Criteria | Defines how quality will be judged
Quality Method | Explains how criteria will be tested

## Configuration Item Records
ID | Unique identifier of the configuration item
Name | Product name or label
Version | Specifies the version of the product
Status | Shows current approval or development status
Relationships | Indicates dependencies or associations with other items

## Change Log
Change ID | Unique identifier for each change request
Description | Outlines the change proposed
Impact | Summarizes expected impact on project objectives
Decision | Records approval, rejection or deferral
Status | Shows progress of the change request

## End Project Report
Project Performance | Summarizes actual vs. planned performance
Business Case Review | Confirms ongoing viability of the project
Product Performance | Assesses whether products met quality and acceptance criteria
Lessons | Captures key learning for future projects
Follow-on Actions | Lists outstanding tasks or recommendations

## End Stage Report
Stage Performance | Summarizes actual vs. planned performance for the stage
Issues and Risks | Highlights key issues or risks for consideration
Lessons | Notes lessons learned during the stage
Next Stage Recommendations | Advises whether to proceed to the next stage

## Lessons Report
Lesson Summary | Provides overview of lessons learned
Positive Lessons | Identifies practices that worked well
Negative Lessons | Describes areas that need improvement
Recommendations | Suggests how lessons should be applied in the future

## Benefits Review Plan
Purpose | Defines how benefits will be tracked after project closure
Responsibilities | Names those accountable for benefit reviews
Timing | Specifies when benefit reviews will be conducted
Methods | Explains how benefits will be measured and reported
Resources | Lists resources needed for review activities