## Project Brief
Background | The company currently uses disconnected tools (Salesforce, Mailchimp, Zendesk) causing inefficiency and poor data visibility
Objectives | Implement HubSpot Hubs to centralize CRM, marketing automation, sales pipeline, service tickets and data operations
Scope | Includes CRM migration, lead lifecycle setup, marketing workflows, sales automation, service ticket pipelines, Ops Hub data syncs; excludes ERP integration
Constraints | Budget of €350k, deadline Q4, limited IT staff availability, compliance with GDPR and ISO27001 required
Assumptions | CRM data is exportable; all teams will adopt HubSpot; HubSpot partner supports migration; SSO can be integrated
Tolerances | Time ±2 weeks, budget ±10%, no tolerance for data loss or GDPR breaches
Outline Business Case | Unify data, reduce software costs, improve pipeline velocity and enhance customer experience with faster service resolution
Project Product Description | A live HubSpot instance fully configured with all four hubs, migrated data, automated workflows and reporting dashboards
Approach | Phased rollout: Marketing Hub → Sales Hub → Service Hub → Ops Hub, with pilot teams before full deployment
Team Structure | Sponsor: CRO; PM: RevOps Manager; Team: Marketing Ops Lead, Sales Ops Lead, Service Manager, Data Architect, HubSpot Partner Consultant

## Project Product Description
Purpose | Provide a single platform to manage marketing, sales, service and operations seamlessly
Composition | CRM database, marketing workflows, sales pipeline automation, service ticketing, data sync integrations
Derivation | Based on user requirements workshops, current pain points and HubSpot’s standard best practices
Quality Expectations | Accurate 360° customer view, reliable automation and adoption by at least 85% of target users within 3 months
Acceptance Criteria | All critical workflows tested, dashboards live data migrated with <1% error, end-user sign-off
Acceptance Method | Conduct UAT with pilot teams, gather sign-offs, verify live dashboards match migrated data

## Daily Log
Date | 2024-10-05
Informal Issues | Email template tokens not resolving during testing
Risks/Opportunities | Risk: API rate limits could slow data sync; Opportunity: deprecate Mailchimp subscription
Decisions | Chose unified deal stage naming across Sales and Marketing for consistency
Observations | Sales team reported better visibility of Marketing contacts in HubSpot CRM

## Lessons Log
Lesson ID | L-001
Lesson | Start email domain warm-up 6 weeks before Marketing Hub launch
Source | Marketing Hub UAT revealed deliverability issues
Application | Apply warm-up practice to future rollouts in other regions

## Business Case
Reasons | Multiple disconnected systems create inefficiency and data silos
Business Options | Option 1: Do nothing; Option 2: Minimal integrations; Option 3: Full HubSpot rollout (recommended)
Expected Benefits | 20% faster lead conversion, 15% faster sales cycles, improved CSAT by 10%
Expected Dis-benefits | Initial productivity dip during migration and training
Timescale | 6 months phased rollout with overlapping enablement
Costs | €350k covering licenses, partner services, training, and contingency
Investment Appraisal | Payback expected within 12 months through cost savings and improved pipeline velocity
Major Risks | Poor data quality, user adoption resistance, third-party integration delays

## Benefits Management Approach
Benefit Profiles | Example: ‘Faster Sales Cycle’ measured by reducing avg close time from 20 to 15 days
Responsibilities | CRO owns revenue KPIs; Head of CS owns CSAT; RevOps measures adoption
Timescales | Quarterly reviews in year 1; annual reviews after stabilization
Methods | HubSpot dashboards and CSAT survey data linked to CRM records
Review Plan | Formal reviews at 3, 6, and 12 months post-launch

## Project Initiation Documentatio
Project Definition | Roll out HubSpot as the single GTM platform to unify marketing, sales, service and ops data
Project Approach | Phased rollout by hub with iterative enablement and UAT for each stage
Business Case | Consolidate tech stack, accelerate pipeline, improve retention via HubSpot adoption
Management Strategies | Risk tracked in HubSpot Ops dashboards, quality via UAT, change via Jira tickets, communication via weekly HubSpot newsletters
Project Plan | Overall timeline of 6 months with milestones per hub
Team Structure | PM, Hub Leads (Marketing/Sales/Service/Ops), RevOps, external HubSpot Partner
Tailoring | Lighter documentation, leverage HubSpot tasks for day-to-day logs

## Project Plan
Plan Description | Deliver HubSpot hubs in phases with clear dependencies
Prerequisites | Domain verified, CRM data cleaned, SSO set up
External Dependencies | Finance system integration, ERP for data sync
Assumptions | Stakeholders will complete UAT within agreed timeframe
PBS | HubSpot Core → Marketing Hub → Sales Hub → Service Hub → Ops Hub
Product Descriptions | Each hub deliverable defined with acceptance criteria
Product Flow | Migrate → Configure → Test → Train → Deploy
Schedule | Q1: Marketing, Q2: Sales, Q3: Service/Ops
Resources | RevOps team, HubSpot partner consultants, Hub leads
Budget | €350k total project spend with contingency
Tolerances | ±2 weeks, ±10% cost
Controls | Weekly progress reporting in HubSpot dashboards

## Stage Plan
Purpose | Define detailed plan for Sales Hub rollout
Products | Sales pipeline, playbooks, reporting dashboards
Schedule | 4 sprints over 8 weeks with final UAT at end
Resources | Sales Ops, RevOps, HubSpot partner
Tolerances | ±1 week allowed

## Team Plan
Purpose | Delivery plan for Marketing Ops team
Products | Email workflows, lead scoring, landing pages
Activities | Design → Configure → QA → UAT
Resources | Marketing Ops lead, designer, RevOps analyst
Schedule | 4 weeks total with weekly milestones

## Communication Management Approa
Stakeholders | C-suite, hub leads, IT, RevOps, end-users
Information Needs | Weekly status, monthly KPI progress, issue alerts
Methods | HubSpot email updates, dashboards, Slack integration
Frequency | Weekly to project team, monthly to board

## Configuration Management Approa
Procedure | All changes tracked via Jira, versions documented in Confluence
Tools | HubSpot Sandboxes, Ops Hub data sync, GitHub for custom code
Records | Maintain version log of workflows, assets and pipelines
Responsibilities | RevOps manages config, IT secures access, Partner ensures documentation

## Quality Management Approach
Standards | GDPR, ISO27001, HubSpot best practices
Responsibilities | QA led by RevOps, verified by Hub Leads
Control Techniques | UAT checklists, automated test emails, sandbox reviews
Records | QA logs stored in Confluence, test reports in HubSpot tickets

## Risk Management Approach
Tolerances | No tolerance for GDPR breach, moderate tolerance for minor delays
Roles | RevOps monitors, PM escalates, board decides major mitigations
Procedures | Weekly risk reviews, risk log updates in HubSpot Ops dashboards
Reporting | Top 5 risks highlighted in monthly board reports

## Change Control Approach
Change Authority | Project Board approves major changes, PM approves minor
Procedure | Submit Jira change ticket, impact assessed, decision logged
Records | Change log maintained in Confluence, linked to HubSpot workflows
Reporting | Changes summarized in weekly highlight reports

## Checkpoint Report
Work Package Progress
Quality Information
Problems and Issues
Forecast

## Highlight Report
Stage Progress | Marketing Hub 100% complete, Sales Hub 70%, Service Hub not started
Risks/Issues | Open risk: data sync delays; Issue: lead routing misconfig
Next Period Forecast | Complete Sales Hub UAT, start Service Hub training
Overall Status | Amber - schedule pressure, benefits intact

## Issue Report
Description | Service tickets not auto-assigning due to workflow misconfiguration
Impact | Delays in customer response, CSAT risk
Options | Option 1: Quick patch; Option 2: Redesign workflow; Option 3: Manual assignment interim
Recommendation | Apply quick patch and redesign in next sprint

## Risk Register
Risk ID | R-001
Description | Integration with finance system may fail
Cause | Finance API poorly documented and unstable
Impact | Billing workflows delayed, manual work required
Probability | Medium
Response | Run early pilot, allocate buffer, coordinate with finance vendor
Owner | Ops Integration Lea
Status | Open - mitigation ongoing

## Issue Register
Issue ID | I-001
Description | HubSpot workflow misrouted leads to inactive owners
Impact | Delays in lead follow-up, risk of lost opportunities
Owner | Sales Ops Manager
Priority | High
Status | Resolved - workflow corrected

## Quality Register
Activity | Email workflow QA review
Product | Onboarding nurture sequence
Date | 2025-08-25
Outcome | All links functional, personalization tokens correct
Follow-up | Schedule quarterly QA of workflows

## Product Descriptions
Purpose | Enable automated lead nurturing
Composition | 4-email sequence with triggers and personalization
Derivation | Based on MQL-to-SQL conversion data and sales feedback
Format | HTML templates with HubSpot tokens
Quality Criteria | Open rate >30%, CTR >5%
Quality Method | Test sends, spam checks, A/B tests

## Configuration Item Records
ID | CIR-101
Name | Sales pipeline workflow
Version | v1.2
Status | Active
Relationships | Depends on lifecycle stage properties
Location | HubSpot Sales Hub instance

## Change Log
Change ID | CH-001
Description | Add custom property for product interest
Impact | Improves segmentation, requires data migration
Decision | Approved by PM, minor change
Status | Implemented
Date | 2024-08-20

## End Project Report
Performance vs Plan | Delivered within budget, delayed by 2 weeks due to integration issues
Business Case Review | Achieved +22% lead conversion and +15% CSAT, payback realized in 10 months
Product Performance | HubSpot adoption at 90% with stable automation and reporting dashboards
Lessons | Earlier data cleansing would have reduced migration delays
Follow-on Actions | Enable AI features in Sales Hub; quarterly adoption refresh training

## End Stage Report
Stage Performance | Sales Hub rolled out 2 weeks late but within budget
Issues/Risks | Open risk: API quota; Closed issue: lead routing fixed
Lessons | Earlier UAT involvement avoids late defects
Next Stage Recommendation | Proceed to Service Hub rollout

## Lessons Report
Summary | Project captured 15 key lessons across hubs
Positives | Staged rollout improved adoption, dashboards boosted transparency
Negatives | Data quality issues delayed migration, underestimated training needs
Recommendations | Run early data audits, extend training, pilot workflows earlier

## Benefits Review Plan
Purpose | Verify benefits realization post-project
Responsibilities | CRO tracks revenue, CS tracks CSAT, RevOps tracks adoption
Timing | Reviews at +3, +6, +12 months post go-live
Methods | HubSpot dashboards, surveys, pipeline metrics
Resources | RevOps analyst time, HubSpot reporting tools